## Whole Project Gantt
GeneAir Research Project ¦ Whole Project Gantt Chart
Project | GeneAir | Start | 2026-06-03 | End | 2027-04-30 | Current Date | 2026-08-28
Timeline | Weekly | Duration | 332 | Status | Research & Development | Total Tasks | 39 | Project Timeline (Weeks)
 | time axis 2026-06-03 to 2027-04-28
Phase | WBS | WBS Task Name | Start | End | Duration | Scope | Milestone | time axis 2026-06-03 to 2027-04-28
Group Registration | '1.1 | Initial Scoping | 2026-06-03 | 2026-06-16 | 14 | Whole Team | bar: 2026-06-03 to 2026-06-10
Group Registration | '1.2 | Administrative Setup | 2026-06-10 | 2026-06-23 | 14 | Whole Team | bar: 2026-06-10 to 2026-06-17
Group Registration | '1.3 | Topic Approval | 2026-06-24 | 2026-07-06 | 13 | Whole Team | Topic Accepted | bar: 2026-06-24 to 2026-07-01
Project Proposal | '2.1 | Literature Planning & Review | 2026-06-10 | 2026-07-18 | 39 | Whole Team | bar: 2026-06-10 to 2026-07-15
Project Proposal | '2.2 | Research Problem & Gap Analysis | 2026-06-17 | 2026-07-25 | 39 | Whole Team | bar: 2026-06-17 to 2026-07-22
Project Proposal | '2.3 | Research Questions & Hypotheses | 2026-07-02 | 2026-08-10 | 40 | Whole Team | bar: 2026-07-01 to 2026-08-05
Project Proposal | '2.4 | Dataset & Resource Planning | 2026-07-15 | 2026-08-25 | 42 | Whole Team | bar: 2026-07-15 to 2026-08-19
Project Proposal | '2.5 | Whole System Architecture Design | 2026-07-20 | 2026-08-25 | 37 | Whole Team | bar: 2026-07-15 to 2026-08-19
Project Proposal | '2.6 | Proposal Preparation | 2026-08-08 | 2026-08-31 | 24 | Whole Team | bar: 2026-08-05 to 2026-08-26
Project Proposal | '2.7 | Proposal Presentation | 2026-09-02 | 2026-09-02 | 1 | Whole Team | Proposal Presented | bar: 2026-09-02
Project Proposal | '2.8 | Proposal Report Submission | 2026-09-15 | 2026-09-15 | 1 | Whole Team | Proposal Submitted | bar: 2026-09-09
PP1 Stage | '3.1 | Dataset Collection, Versioning & Documentation | 2026-06-23 | 2026-09-15 | 85 | Whole Team | bar: 2026-06-17 to 2026-09-09
PP1 Stage | '3.2 | Common Data Cleaning & Patient-Level Alignment | 2026-08-20 | 2026-09-25 | 37 | Whole Team | bar: 2026-08-19 to 2026-09-23
PP1 Stage | '3.3 | Component 1 Baseline & Stream Preparation | 2026-09-01 | 2026-10-23 | 53 | C1 | bar: 2026-08-26 to 2026-10-21
PP1 Stage | '3.4 | Component 2 SHAP / XAI Baseline Pipeline | 2026-09-16 | 2026-10-23 | 38 | C2 | bar: 2026-09-16 to 2026-10-21
PP1 Stage | '3.5 | Component 3 IoT Sensor Pipeline | 2026-09-01 | 2026-10-13 | 43 | C3 | bar: 2026-08-26 to 2026-10-07
PP1 Stage | '3.6 | Component 4 RAG Knowledge Base & Retrieval Baseline | 2026-09-09 | 2026-10-20 | 42 | C4 | bar: 2026-09-09 to 2026-10-14
PP1 Stage | '3.7 | Progress Presentation 01 | 2026-10-26 | 2026-10-26 | 1 | Whole Team | PP1 Presentation | bar: 2026-10-21
PP1 Stage | '3.8 | PP1 Report & Checklist Submission | 2026-10-30 | 2026-10-30 | 1 | Whole Team | PP1 Submitted | bar: 2026-10-28
Testing & Control | '4.1 | Progress & Milestone Control | 2026-09-01 | 2027-01-31 | 153 | Whole Team | bar: 2026-08-26 to 2027-01-27
Testing & Control | '4.2 | Pipeline / Unit / Integration Testing | 2026-10-01 | 2027-01-31 | 123 | Whole Team | bar: 2026-09-30 to 2027-01-27
Testing & Control | '4.3 | Data Leakage & Quality Control | 2026-09-15 | 2027-01-31 | 139 | Whole Team | bar: 2026-09-09 to 2027-01-27
Testing & Control | '4.4 | Risk, Ethics, Safety & Privacy Review | 2026-09-15 | 2027-01-31 | 139 | Whole Team | bar: 2026-09-09 to 2027-01-27
Testing & Control | '4.5 | Documentation & Logbook Maintenance | 2026-07-01 | 2027-03-31 | 274 | Whole Team | bar: 2026-07-01 to 2027-03-31
PP2 Stage | '5.1 | C1 Stream Models, TVL & Meta-XGBoost | 2026-09-15 | 2026-12-20 | 97 | C1 | bar: 2026-09-09 to 2026-12-16
PP2 Stage | '5.2 | C2 Hierarchical XAI & Counterfactual Engine | 2026-10-15 | 2026-12-31 | 78 | C2 | bar: 2026-10-14 to 2026-12-30
PP2 Stage | '5.3 | C3 State-Trend Representation & Device Integration | 2026-10-15 | 2026-12-31 | 78 | C3 | bar: 2026-10-14 to 2026-12-30
PP2 Stage | '5.4 | C4 Genotype/Context-Grounded Corrective RAG | 2026-10-15 | 2026-12-31 | 78 | C4 | bar: 2026-10-14 to 2026-12-30
PP2 Stage | '5.5 | End-to-End GeneAir Integration | 2026-12-01 | 2027-01-10 | 41 | Whole Team | bar: 2026-11-25 to 2027-01-06
PP2 Stage | '5.6 | Ablation, Robustness & Staleness Experiments | 2026-12-01 | 2027-01-15 | 46 | C1 | bar: 2026-11-25 to 2027-01-13
PP2 Stage | '5.7 | Evaluation & Statistical Analysis | 2026-12-15 | 2027-01-31 | 48 | Whole Team | bar: 2026-12-09 to 2027-01-27
PP2 Stage | '5.8 | PP2 Presentation & Report | 2027-01-20 | 2027-01-31 | 12 | Whole Team | PP2 Complete | bar: 2027-01-20 to 2027-01-27
Final Stage | '6.1 | Model & System Finalization | 2027-01-15 | 2027-02-15 | 32 | Whole Team | bar: 2027-01-13 to 2027-02-10
Final Stage | '6.2 | Mobile App & Doctor Portal Final Integration | 2027-01-15 | 2027-02-28 | 45 | Whole Team | bar: 2027-01-13 to 2027-02-24
Final Stage | '6.3 | Final System Validation & Demo Testing | 2027-02-15 | 2027-03-15 | 29 | Whole Team | bar: 2027-02-10 to 2027-03-10
Final Stage | '6.4 | Individual Research Paper Writing | 2027-01-15 | 2027-03-31 | 76 | Each Member | bar: 2027-01-13 to 2027-03-31
Final Stage | '6.5 | Final Documentation & Appendices | 2027-03-01 | 2027-04-15 | 46 | Whole Team | bar: 2027-02-24 to 2027-04-14
Final Stage | '6.6 | Final Presentation & Viva Preparation | 2027-03-15 | 2027-04-20 | 37 | Whole Team | bar: 2027-03-10 to 2027-04-14
Final Stage | '6.7 | Final Submission / Assessment | 2027-04-20 | 2027-04-30 | 11 | Whole Team | Project Complete | bar: 2027-04-14 to 2027-04-28

## Component-wise Gantt
GeneAir ¦ Component-wise Gantt Chart
Project | GeneAir | Components | 4 | Start | 2026-06-03 | End
Current Date | 2026-08-28 | Timeline | Weekly | Final Date | 2027-04-30 |  | Project Timeline (Weeks)
 | time axis 2026-06-03 to 2027-04-28
Component | WBS | Task | Start | End | Duration | Work Area | time axis 2026-06-03 to 2027-04-28
C1 ¦ TVL Multi-Rate Multimodal Risk Prediction
C1 | '1.1 | Literature Review: Multi-rate Fusion & Temporal Validity | 2026-06-10 | 2026-08-20 | 72 | Research | bar: 2026-06-10 to 2026-08-19
C1 | '1.2 | Dataset Selection & Stream Definition | 2026-07-15 | 2026-09-05 | 53 | Data | bar: 2026-07-15 to 2026-09-02
C1 | '1.3 | Clinical / IoT / Medication / Genetics Preparation | 2026-08-20 | 2026-10-13 | 55 | Data | bar: 2026-08-19 to 2026-10-07
C1 | '1.4 | Baseline Stream Models | 2026-09-16 | 2026-10-31 | 46 | ML | bar: 2026-09-16 to 2026-10-28
C1 | '1.5 | Patient-Level K-Fold & OOF Pipeline | 2026-10-01 | 2026-11-15 | 46 | ML | bar: 2026-09-30 to 2026-11-11
C1 | '1.6 | TVL Engine Design & Gamma Calculation | 2026-10-15 | 2026-12-10 | 57 | Novelty | bar: 2026-10-14 to 2026-12-09
C1 | '1.7 | Meta-XGBoost Fusion | 2026-11-01 | 2026-12-20 | 50 | ML | bar: 2026-10-28 to 2026-12-16
C1 | '1.8 | Calibration & Threshold Selection | 2026-12-01 | 2026-12-31 | 31 | Evaluation | bar: 2026-11-25 to 2026-12-30
C1 | '1.9 | AAMOS-00 Baseline Reproduction | 2026-11-15 | 2026-12-20 | 36 | Paper | bar: 2026-11-11 to 2026-12-16
C1 | '1.10 | Staleness Stress Testing | 2026-12-01 | 2027-01-15 | 46 | Paper | bar: 2026-11-25 to 2027-01-13
C1 | '1.11 | Ablation & Statistical Validation | 2026-12-15 | 2027-01-31 | 48 | Evaluation | bar: 2026-12-09 to 2027-01-27
C1 | '1.12 | Component Integration & API | 2027-01-01 | 2027-02-15 | 46 | Integration | bar: 2026-12-30 to 2027-02-10
C1 | '1.13 | Individual Paper Writing | 2027-01-15 | 2027-03-31 | 76 | Paper | bar: 2027-01-13 to 2027-03-31
C2 ¦ Hierarchical Explainable Asthma Risk Alerting
C2 | '2.1 | Literature Review: XAI & Clinical Explainability | 2026-06-10 | 2026-08-20 | 72 | Research | bar: 2026-06-10 to 2026-08-19
C2 | '2.2 | SHAP Baseline for Stream Models | 2026-09-16 | 2026-10-23 | 38 | XAI | bar: 2026-09-16 to 2026-10-21
C2 | '2.3 | Meta-Model SHAP Explanation | 2026-10-15 | 2026-11-20 | 37 | XAI | bar: 2026-10-14 to 2026-11-18
C2 | '2.4 | Cross-Level Explanation Reconciliation | 2026-11-01 | 2026-12-10 | 40 | Novelty | bar: 2026-10-28 to 2026-12-09
C2 | '2.5 | Feature Stability & Recency Weighting | 2026-11-10 | 2026-12-20 | 41 | Novelty | bar: 2026-11-04 to 2026-12-16
C2 | '2.6 | Actionable vs Irremovable Feature Classification | 2026-11-20 | 2026-12-31 | 42 | XAI | bar: 2026-11-18 to 2026-12-30
C2 | '2.7 | Counterfactual Candidate Generation | 2026-12-01 | 2027-01-15 | 46 | XAI | bar: 2026-11-25 to 2027-01-13
C2 | '2.8 | Safety / Cost Evaluation of Counterfactuals | 2026-12-10 | 2027-01-31 | 53 | Safety | bar: 2026-12-09 to 2027-01-27
C2 | '2.9 | LLM Narration & Dashboard Explanation | 2027-01-01 | 2027-02-15 | 46 | Integration | bar: 2026-12-30 to 2027-02-10
C2 | '2.10 | User Explanation Evaluation | 2027-02-01 | 2027-03-15 | 43 | Evaluation | bar: 2027-01-27 to 2027-03-10
C2 | '2.11 | Individual Paper Writing | 2027-01-15 | 2027-03-31 | 76 | Paper | bar: 2027-01-13 to 2027-03-31
C3 ¦ Multi-Rate Wearable Signal Processing with State & Trend Representation
C3 | '3.1 | Literature Review: Wearable Signal Processing | 2026-06-10 | 2026-08-20 | 72 | Research | bar: 2026-06-10 to 2026-08-19
C3 | '3.2 | IoT Hardware & Sensor Selection | 2026-07-01 | 2026-08-31 | 62 | Hardware | bar: 2026-07-01 to 2026-08-26
C3 | '3.3 | Sensor Data Acquisition Firmware | 2026-08-01 | 2026-09-30 | 61 | Hardware | bar: 2026-07-29 to 2026-09-30
C3 | '3.4 | Fast / Medium / Slow Signal Filters | 2026-09-01 | 2026-10-13 | 43 | Signal | bar: 2026-08-26 to 2026-10-07
C3 | '3.5 | Windowing & Feature Extraction | 2026-09-15 | 2026-10-31 | 47 | Signal | bar: 2026-09-09 to 2026-10-28
C3 | '3.6 | Regression-Based Trend Extraction | 2026-10-01 | 2026-11-15 | 46 | Novelty | bar: 2026-09-30 to 2026-11-11
C3 | '3.7 | Aggregation & Z-Score Normalization | 2026-10-15 | 2026-11-30 | 47 | Signal | bar: 2026-10-14 to 2026-11-25
C3 | '3.8 | LSTM State-Trend Representation | 2026-11-01 | 2026-12-31 | 61 | ML | bar: 2026-10-28 to 2026-12-30
C3 | '3.9 | Device-to-API Gateway Integration | 2026-11-15 | 2027-01-15 | 62 | Integration | bar: 2026-11-11 to 2027-01-13
C3 | '3.10 | Sensor Reliability & Stress Testing | 2026-12-01 | 2027-02-15 | 77 | Testing | bar: 2026-11-25 to 2027-02-10
C3 | '3.11 | Individual Paper Writing | 2027-01-15 | 2027-03-31 | 76 | Paper | bar: 2027-01-13 to 2027-03-31
C4 ¦ Context-Aware RAG Asthma Management Assistant
C4 | '4.1 | Literature Review: RAG, CRAG & PGxRAG | 2026-06-10 | 2026-08-20 | 72 | Research | bar: 2026-06-10 to 2026-08-19
C4 | '4.2 | Trusted Knowledge Source Collection | 2026-08-01 | 2026-09-30 | 61 | Knowledge | bar: 2026-07-29 to 2026-09-30
C4 | '4.3 | Document Cleaning, Chunking & Metadata | 2026-09-01 | 2026-10-15 | 45 | RAG | bar: 2026-08-26 to 2026-10-14
C4 | '4.4 | Embedding & ChromaDB Indexing | 2026-09-15 | 2026-10-31 | 47 | RAG | bar: 2026-09-09 to 2026-10-28
C4 | '4.5 | Baseline RAG Retrieval | 2026-10-01 | 2026-11-15 | 46 | RAG | bar: 2026-09-30 to 2026-11-11
C4 | '4.6 | Genetic + Clinical Context Manager | 2026-10-15 | 2026-12-01 | 48 | Novelty | bar: 2026-10-14 to 2026-11-25
C4 | '4.7 | Query Understanding / Decomposition | 2026-11-01 | 2026-12-15 | 45 | Novelty | bar: 2026-10-28 to 2026-12-09
C4 | '4.8 | Corrective Retrieval & Confidence Gate | 2026-11-15 | 2027-01-15 | 62 | Novelty | bar: 2026-11-11 to 2027-01-13
C4 | '4.9 | Reranking & Evidence Grounding | 2026-12-01 | 2027-01-20 | 51 | RAG | bar: 2026-11-25 to 2027-01-20
C4 | '4.10 | LLM Generation & Safety Checks | 2026-12-15 | 2027-02-15 | 63 | Safety | bar: 2026-12-09 to 2027-02-10
C4 | '4.11 | RAGAS / Retrieval Evaluation | 2027-01-15 | 2027-03-01 | 46 | Evaluation | bar: 2027-01-13 to 2027-02-24
C4 | '4.12 | GeneAir App / Portal Integration | 2027-01-20 | 2027-02-28 | 40 | Integration | bar: 2027-01-20 to 2027-02-24
C4 | '4.13 | Individual Paper Writing | 2027-01-15 | 2027-03-31 | 76 | Paper | bar: 2027-01-13 to 2027-03-31

## Whole WBS
GeneAir ¦ Whole Project Work Breakdown Structure
WBS | Phase | Task / Work Package | Scope | Start | End | Duration (Days) | Deliverable / Milestone
'1.1 | Group Registration | Initial Scoping | Whole Team | 2026-06-03 | 2026-06-16 | 14
'1.2 | Group Registration | Administrative Setup | Whole Team | 2026-06-10 | 2026-06-23 | 14
'1.3 | Group Registration | Topic Approval | Whole Team | 2026-06-24 | 2026-07-06 | 13 | Topic Accepted
'2.1 | Project Proposal | Literature Planning & Review | Whole Team | 2026-06-10 | 2026-07-18 | 39
'2.2 | Project Proposal | Research Problem & Gap Analysis | Whole Team | 2026-06-17 | 2026-07-25 | 39
'2.3 | Project Proposal | Research Questions & Hypotheses | Whole Team | 2026-07-02 | 2026-08-10 | 40
'2.4 | Project Proposal | Dataset & Resource Planning | Whole Team | 2026-07-15 | 2026-08-25 | 42
'2.5 | Project Proposal | Whole System Architecture Design | Whole Team | 2026-07-20 | 2026-08-25 | 37
'2.6 | Project Proposal | Proposal Preparation | Whole Team | 2026-08-08 | 2026-08-31 | 24
'2.7 | Project Proposal | Proposal Presentation | Whole Team | 2026-09-02 | 2026-09-02 | 1 | Proposal Presented
'2.8 | Project Proposal | Proposal Report Submission | Whole Team | 2026-09-15 | 2026-09-15 | 1 | Proposal Submitted
'3.1 | PP1 Stage | Dataset Collection, Versioning & Documentation | Whole Team | 2026-06-23 | 2026-09-15 | 85
'3.2 | PP1 Stage | Common Data Cleaning & Patient-Level Alignment | Whole Team | 2026-08-20 | 2026-09-25 | 37
'3.3 | PP1 Stage | Component 1 Baseline & Stream Preparation | C1 | 2026-09-01 | 2026-10-23 | 53
'3.4 | PP1 Stage | Component 2 SHAP / XAI Baseline Pipeline | C2 | 2026-09-16 | 2026-10-23 | 38
'3.5 | PP1 Stage | Component 3 IoT Sensor Pipeline | C3 | 2026-09-01 | 2026-10-13 | 43
'3.6 | PP1 Stage | Component 4 RAG Knowledge Base & Retrieval Baseline | C4 | 2026-09-09 | 2026-10-20 | 42
'3.7 | PP1 Stage | Progress Presentation 01 | Whole Team | 2026-10-26 | 2026-10-26 | 1 | PP1 Presentation
'3.8 | PP1 Stage | PP1 Report & Checklist Submission | Whole Team | 2026-10-30 | 2026-10-30 | 1 | PP1 Submitted
'4.1 | Testing & Control | Progress & Milestone Control | Whole Team | 2026-09-01 | 2027-01-31 | 153
'4.2 | Testing & Control | Pipeline / Unit / Integration Testing | Whole Team | 2026-10-01 | 2027-01-31 | 123
'4.3 | Testing & Control | Data Leakage & Quality Control | Whole Team | 2026-09-15 | 2027-01-31 | 139
'4.4 | Testing & Control | Risk, Ethics, Safety & Privacy Review | Whole Team | 2026-09-15 | 2027-01-31 | 139
'4.5 | Testing & Control | Documentation & Logbook Maintenance | Whole Team | 2026-07-01 | 2027-03-31 | 274
'5.1 | PP2 Stage | C1 Stream Models, TVL & Meta-XGBoost | C1 | 2026-09-15 | 2026-12-20 | 97
'5.2 | PP2 Stage | C2 Hierarchical XAI & Counterfactual Engine | C2 | 2026-10-15 | 2026-12-31 | 78
'5.3 | PP2 Stage | C3 State-Trend Representation & Device Integration | C3 | 2026-10-15 | 2026-12-31 | 78
'5.4 | PP2 Stage | C4 Genotype/Context-Grounded Corrective RAG | C4 | 2026-10-15 | 2026-12-31 | 78
'5.5 | PP2 Stage | End-to-End GeneAir Integration | Whole Team | 2026-12-01 | 2027-01-10 | 41
'5.6 | PP2 Stage | Ablation, Robustness & Staleness Experiments | C1 | 2026-12-01 | 2027-01-15 | 46
'5.7 | PP2 Stage | Evaluation & Statistical Analysis | Whole Team | 2026-12-15 | 2027-01-31 | 48
'5.8 | PP2 Stage | PP2 Presentation & Report | Whole Team | 2027-01-20 | 2027-01-31 | 12 | PP2 Complete
'6.1 | Final Stage | Model & System Finalization | Whole Team | 2027-01-15 | 2027-02-15 | 32
'6.2 | Final Stage | Mobile App & Doctor Portal Final Integration | Whole Team | 2027-01-15 | 2027-02-28 | 45
'6.3 | Final Stage | Final System Validation & Demo Testing | Whole Team | 2027-02-15 | 2027-03-15 | 29
'6.4 | Final Stage | Individual Research Paper Writing | Each Member | 2027-01-15 | 2027-03-31 | 76
'6.5 | Final Stage | Final Documentation & Appendices | Whole Team | 2027-03-01 | 2027-04-15 | 46
'6.6 | Final Stage | Final Presentation & Viva Preparation | Whole Team | 2027-03-15 | 2027-04-20 | 37
'6.7 | Final Stage | Final Submission / Assessment | Whole Team | 2027-04-20 | 2027-04-30 | 11 | Project Complete

## C1 WBS
C1 ¦ TVL Multi-Rate Multimodal Risk Prediction ¦ Work Breakdown Structure
Component | C1 | Research Component | TVL Multi-Rate Multimodal Risk Prediction | Start | 2026-06-03 | End | 2027-04-30
WBS | Task / Work Package | Work Area | Start | End | Duration (Days) | Key Output | Status
'1.1 | Literature Review: Multi-rate Fusion & Temporal Validity | Research | 2026-06-10 | 2026-08-20 | 72 | Literature synthesis / gap | Planned
'1.2 | Dataset Selection & Stream Definition | Data | 2026-07-15 | 2026-09-05 | 53 | Prepared component dataset | Planned
'1.3 | Clinical / IoT / Medication / Genetics Preparation | Data | 2026-08-20 | 2026-10-13 | 55 | Prepared component dataset | Planned
'1.4 | Baseline Stream Models | ML | 2026-09-16 | 2026-10-31 | 46 | Trained model / pipeline | Planned
'1.5 | Patient-Level K-Fold & OOF Pipeline | ML | 2026-10-01 | 2026-11-15 | 46 | Trained model / pipeline | Planned
'1.6 | TVL Engine Design & Gamma Calculation | Novelty | 2026-10-15 | 2026-12-10 | 57 | Proposed method implementation | Planned
'1.7 | Meta-XGBoost Fusion | ML | 2026-11-01 | 2026-12-20 | 50 | Trained model / pipeline | Planned
'1.8 | Calibration & Threshold Selection | Evaluation | 2026-12-01 | 2026-12-31 | 31 | Metrics / statistical results | Planned
'1.9 | AAMOS-00 Baseline Reproduction | Paper | 2026-11-15 | 2026-12-20 | 36 | Individual research paper | Planned
'1.10 | Staleness Stress Testing | Paper | 2026-12-01 | 2027-01-15 | 46 | Individual research paper | Planned
'1.11 | Ablation & Statistical Validation | Evaluation | 2026-12-15 | 2027-01-31 | 48 | Metrics / statistical results | Planned
'1.12 | Component Integration & API | Integration | 2027-01-01 | 2027-02-15 | 46 | Integrated API / module | Planned
'1.13 | Individual Paper Writing | Paper | 2027-01-15 | 2027-03-31 | 76 | Individual research paper | Planned

## C2 WBS
C2 ¦ Hierarchical Explainable Asthma Risk Alerting ¦ Work Breakdown Structure
Component | C2 | Research Component | Hierarchical Explainable Asthma Risk Alerting | Start | 2026-06-03 | End | 2027-04-30
WBS | Task / Work Package | Work Area | Start | End | Duration (Days) | Key Output | Status
'2.1 | Literature Review: XAI & Clinical Explainability | Research | 2026-06-10 | 2026-08-20 | 72 | Literature synthesis / gap | Planned
'2.2 | SHAP Baseline for Stream Models | XAI | 2026-09-16 | 2026-10-23 | 38 | Explanation module | Planned
'2.3 | Meta-Model SHAP Explanation | XAI | 2026-10-15 | 2026-11-20 | 37 | Explanation module | Planned
'2.4 | Cross-Level Explanation Reconciliation | Novelty | 2026-11-01 | 2026-12-10 | 40 | Proposed method implementation | Planned
'2.5 | Feature Stability & Recency Weighting | Novelty | 2026-11-10 | 2026-12-20 | 41 | Proposed method implementation | Planned
'2.6 | Actionable vs Irremovable Feature Classification | XAI | 2026-11-20 | 2026-12-31 | 42 | Explanation module | Planned
'2.7 | Counterfactual Candidate Generation | XAI | 2026-12-01 | 2027-01-15 | 46 | Explanation module | Planned
'2.8 | Safety / Cost Evaluation of Counterfactuals | Safety | 2026-12-10 | 2027-01-31 | 53 | Validated safety rules | Planned
'2.9 | LLM Narration & Dashboard Explanation | Integration | 2027-01-01 | 2027-02-15 | 46 | Integrated API / module | Planned
'2.10 | User Explanation Evaluation | Evaluation | 2027-02-01 | 2027-03-15 | 43 | Metrics / statistical results | Planned
'2.11 | Individual Paper Writing | Paper | 2027-01-15 | 2027-03-31 | 76 | Individual research paper | Planned

## C3 WBS
C3 ¦ Multi-Rate Wearable Signal Processing with State & Trend Representation ¦ Work Breakdown Structure
Component | C3 | Research Component | Multi-Rate Wearable Signal Processing with State & Trend Representation | Start | 2026-06-03 | End | 2027-04-30
WBS | Task / Work Package | Work Area | Start | End | Duration (Days) | Key Output | Status
'3.1 | Literature Review: Wearable Signal Processing | Research | 2026-06-10 | 2026-08-20 | 72 | Literature synthesis / gap | Planned
'3.2 | IoT Hardware & Sensor Selection | Hardware | 2026-07-01 | 2026-08-31 | 62 | Working IoT prototype | Planned
'3.3 | Sensor Data Acquisition Firmware | Hardware | 2026-08-01 | 2026-09-30 | 61 | Working IoT prototype | Planned
'3.4 | Fast / Medium / Slow Signal Filters | Signal | 2026-09-01 | 2026-10-13 | 43 | Processed sensor features | Planned
'3.5 | Windowing & Feature Extraction | Signal | 2026-09-15 | 2026-10-31 | 47 | Processed sensor features | Planned
'3.6 | Regression-Based Trend Extraction | Novelty | 2026-10-01 | 2026-11-15 | 46 | Proposed method implementation | Planned
'3.7 | Aggregation & Z-Score Normalization | Signal | 2026-10-15 | 2026-11-30 | 47 | Processed sensor features | Planned
'3.8 | LSTM State-Trend Representation | ML | 2026-11-01 | 2026-12-31 | 61 | Trained model / pipeline | Planned
'3.9 | Device-to-API Gateway Integration | Integration | 2026-11-15 | 2027-01-15 | 62 | Integrated API / module | Planned
'3.10 | Sensor Reliability & Stress Testing | Testing | 2026-12-01 | 2027-02-15 | 77 | Test report | Planned
'3.11 | Individual Paper Writing | Paper | 2027-01-15 | 2027-03-31 | 76 | Individual research paper | Planned

## C4 WBS
C4 ¦ Context-Aware RAG Asthma Management Assistant ¦ Work Breakdown Structure
Component | C4 | Research Component | Context-Aware RAG Asthma Management Assistant | Start | 2026-06-03 | End | 2027-04-30
WBS | Task / Work Package | Work Area | Start | End | Duration (Days) | Key Output | Status
'4.1 | Literature Review: RAG, CRAG & PGxRAG | Research | 2026-06-10 | 2026-08-20 | 72 | Literature synthesis / gap | Planned
'4.2 | Trusted Knowledge Source Collection | Knowledge | 2026-08-01 | 2026-09-30 | 61 | Curated knowledge sources | Planned
'4.3 | Document Cleaning, Chunking & Metadata | RAG | 2026-09-01 | 2026-10-15 | 45 | Retrieval / generation pipeline | Planned
'4.4 | Embedding & ChromaDB Indexing | RAG | 2026-09-15 | 2026-10-31 | 47 | Retrieval / generation pipeline | Planned
'4.5 | Baseline RAG Retrieval | RAG | 2026-10-01 | 2026-11-15 | 46 | Retrieval / generation pipeline | Planned
'4.6 | Genetic + Clinical Context Manager | Novelty | 2026-10-15 | 2026-12-01 | 48 | Proposed method implementation | Planned
'4.7 | Query Understanding / Decomposition | Novelty | 2026-11-01 | 2026-12-15 | 45 | Proposed method implementation | Planned
'4.8 | Corrective Retrieval & Confidence Gate | Novelty | 2026-11-15 | 2027-01-15 | 62 | Proposed method implementation | Planned
'4.9 | Reranking & Evidence Grounding | RAG | 2026-12-01 | 2027-01-20 | 51 | Retrieval / generation pipeline | Planned
'4.10 | LLM Generation & Safety Checks | Safety | 2026-12-15 | 2027-02-15 | 63 | Validated safety rules | Planned
'4.11 | RAGAS / Retrieval Evaluation | Evaluation | 2027-01-15 | 2027-03-01 | 46 | Metrics / statistical results | Planned
'4.12 | GeneAir App / Portal Integration | Integration | 2027-01-20 | 2027-02-28 | 40 | Integrated API / module | Planned
'4.13 | Individual Paper Writing | Paper | 2027-01-15 | 2027-03-31 | 76 | Individual research paper | Planned

## Task Register
GeneAir ¦ Master Task Register
Level | Component | WBS | Phase / Area | Task | Start | End | Duration | Milestone | Status
Whole Project | Whole Team | '1.1 | Group Registration | Initial Scoping | 2026-06-03 | 2026-06-16 | 14 |  | Planned
Whole Project | Whole Team | '1.2 | Group Registration | Administrative Setup | 2026-06-10 | 2026-06-23 | 14 |  | Planned
Whole Project | Whole Team | '1.3 | Group Registration | Topic Approval | 2026-06-24 | 2026-07-06 | 13 | Topic Accepted | Planned
Whole Project | Whole Team | '2.1 | Project Proposal | Literature Planning & Review | 2026-06-10 | 2026-07-18 | 39 |  | Planned
Whole Project | Whole Team | '2.2 | Project Proposal | Research Problem & Gap Analysis | 2026-06-17 | 2026-07-25 | 39 |  | Planned
Whole Project | Whole Team | '2.3 | Project Proposal | Research Questions & Hypotheses | 2026-07-02 | 2026-08-10 | 40 |  | Planned
Whole Project | Whole Team | '2.4 | Project Proposal | Dataset & Resource Planning | 2026-07-15 | 2026-08-25 | 42 |  | Planned
Whole Project | Whole Team | '2.5 | Project Proposal | Whole System Architecture Design | 2026-07-20 | 2026-08-25 | 37 |  | Planned
Whole Project | Whole Team | '2.6 | Project Proposal | Proposal Preparation | 2026-08-08 | 2026-08-31 | 24 |  | Planned
Whole Project | Whole Team | '2.7 | Project Proposal | Proposal Presentation | 2026-09-02 | 2026-09-02 | 1 | Proposal Presented | Planned
Whole Project | Whole Team | '2.8 | Project Proposal | Proposal Report Submission | 2026-09-15 | 2026-09-15 | 1 | Proposal Submitted | Planned
Whole Project | Whole Team | '3.1 | PP1 Stage | Dataset Collection, Versioning & Documentation | 2026-06-23 | 2026-09-15 | 85 |  | Planned
Whole Project | Whole Team | '3.2 | PP1 Stage | Common Data Cleaning & Patient-Level Alignment | 2026-08-20 | 2026-09-25 | 37 |  | Planned
Whole Project | C1 | '3.3 | PP1 Stage | Component 1 Baseline & Stream Preparation | 2026-09-01 | 2026-10-23 | 53 |  | Planned
Whole Project | C2 | '3.4 | PP1 Stage | Component 2 SHAP / XAI Baseline Pipeline | 2026-09-16 | 2026-10-23 | 38 |  | Planned
Whole Project | C3 | '3.5 | PP1 Stage | Component 3 IoT Sensor Pipeline | 2026-09-01 | 2026-10-13 | 43 |  | Planned
Whole Project | C4 | '3.6 | PP1 Stage | Component 4 RAG Knowledge Base & Retrieval Baseline | 2026-09-09 | 2026-10-20 | 42 |  | Planned
Whole Project | Whole Team | '3.7 | PP1 Stage | Progress Presentation 01 | 2026-10-26 | 2026-10-26 | 1 | PP1 Presentation | Planned
Whole Project | Whole Team | '3.8 | PP1 Stage | PP1 Report & Checklist Submission | 2026-10-30 | 2026-10-30 | 1 | PP1 Submitted | Planned
Whole Project | Whole Team | '4.1 | Testing & Control | Progress & Milestone Control | 2026-09-01 | 2027-01-31 | 153 |  | Planned
Whole Project | Whole Team | '4.2 | Testing & Control | Pipeline / Unit / Integration Testing | 2026-10-01 | 2027-01-31 | 123 |  | Planned
Whole Project | Whole Team | '4.3 | Testing & Control | Data Leakage & Quality Control | 2026-09-15 | 2027-01-31 | 139 |  | Planned
Whole Project | Whole Team | '4.4 | Testing & Control | Risk, Ethics, Safety & Privacy Review | 2026-09-15 | 2027-01-31 | 139 |  | Planned
Whole Project | Whole Team | '4.5 | Testing & Control | Documentation & Logbook Maintenance | 2026-07-01 | 2027-03-31 | 274 |  | Planned
Whole Project | C1 | '5.1 | PP2 Stage | C1 Stream Models, TVL & Meta-XGBoost | 2026-09-15 | 2026-12-20 | 97 |  | Planned
Whole Project | C2 | '5.2 | PP2 Stage | C2 Hierarchical XAI & Counterfactual Engine | 2026-10-15 | 2026-12-31 | 78 |  | Planned
Whole Project | C3 | '5.3 | PP2 Stage | C3 State-Trend Representation & Device Integration | 2026-10-15 | 2026-12-31 | 78 |  | Planned
Whole Project | C4 | '5.4 | PP2 Stage | C4 Genotype/Context-Grounded Corrective RAG | 2026-10-15 | 2026-12-31 | 78 |  | Planned
Whole Project | Whole Team | '5.5 | PP2 Stage | End-to-End GeneAir Integration | 2026-12-01 | 2027-01-10 | 41 |  | Planned
Whole Project | C1 | '5.6 | PP2 Stage | Ablation, Robustness & Staleness Experiments | 2026-12-01 | 2027-01-15 | 46 |  | Planned
Whole Project | Whole Team | '5.7 | PP2 Stage | Evaluation & Statistical Analysis | 2026-12-15 | 2027-01-31 | 48 |  | Planned
Whole Project | Whole Team | '5.8 | PP2 Stage | PP2 Presentation & Report | 2027-01-20 | 2027-01-31 | 12 | PP2 Complete | Planned
Whole Project | Whole Team | '6.1 | Final Stage | Model & System Finalization | 2027-01-15 | 2027-02-15 | 32 |  | Planned
Whole Project | Whole Team | '6.2 | Final Stage | Mobile App & Doctor Portal Final Integration | 2027-01-15 | 2027-02-28 | 45 |  | Planned
Whole Project | Whole Team | '6.3 | Final Stage | Final System Validation & Demo Testing | 2027-02-15 | 2027-03-15 | 29 |  | Planned
Whole Project | Each Member | '6.4 | Final Stage | Individual Research Paper Writing | 2027-01-15 | 2027-03-31 | 76 |  | Planned
Whole Project | Whole Team | '6.5 | Final Stage | Final Documentation & Appendices | 2027-03-01 | 2027-04-15 | 46 |  | Planned
Whole Project | Whole Team | '6.6 | Final Stage | Final Presentation & Viva Preparation | 2027-03-15 | 2027-04-20 | 37 |  | Planned
Whole Project | Whole Team | '6.7 | Final Stage | Final Submission / Assessment | 2027-04-20 | 2027-04-30 | 11 | Project Complete | Planned
Component | C1 | '1.1 | Research | Literature Review: Multi-rate Fusion & Temporal Validity | 2026-06-10 | 2026-08-20 | 72 |  | Planned
Component | C1 | '1.2 | Data | Dataset Selection & Stream Definition | 2026-07-15 | 2026-09-05 | 53 |  | Planned
Component | C1 | '1.3 | Data | Clinical / IoT / Medication / Genetics Preparation | 2026-08-20 | 2026-10-13 | 55 |  | Planned
Component | C1 | '1.4 | ML | Baseline Stream Models | 2026-09-16 | 2026-10-31 | 46 |  | Planned
Component | C1 | '1.5 | ML | Patient-Level K-Fold & OOF Pipeline | 2026-10-01 | 2026-11-15 | 46 |  | Planned
Component | C1 | '1.6 | Novelty | TVL Engine Design & Gamma Calculation | 2026-10-15 | 2026-12-10 | 57 |  | Planned
Component | C1 | '1.7 | ML | Meta-XGBoost Fusion | 2026-11-01 | 2026-12-20 | 50 |  | Planned
Component | C1 | '1.8 | Evaluation | Calibration & Threshold Selection | 2026-12-01 | 2026-12-31 | 31 |  | Planned
Component | C1 | '1.9 | Paper | AAMOS-00 Baseline Reproduction | 2026-11-15 | 2026-12-20 | 36 |  | Planned
Component | C1 | '1.10 | Paper | Staleness Stress Testing | 2026-12-01 | 2027-01-15 | 46 |  | Planned
Component | C1 | '1.11 | Evaluation | Ablation & Statistical Validation | 2026-12-15 | 2027-01-31 | 48 |  | Planned
Component | C1 | '1.12 | Integration | Component Integration & API | 2027-01-01 | 2027-02-15 | 46 |  | Planned
Component | C1 | '1.13 | Paper | Individual Paper Writing | 2027-01-15 | 2027-03-31 | 76 |  | Planned
Component | C2 | '2.1 | Research | Literature Review: XAI & Clinical Explainability | 2026-06-10 | 2026-08-20 | 72 |  | Planned
Component | C2 | '2.2 | XAI | SHAP Baseline for Stream Models | 2026-09-16 | 2026-10-23 | 38 |  | Planned
Component | C2 | '2.3 | XAI | Meta-Model SHAP Explanation | 2026-10-15 | 2026-11-20 | 37 |  | Planned
Component | C2 | '2.4 | Novelty | Cross-Level Explanation Reconciliation | 2026-11-01 | 2026-12-10 | 40 |  | Planned
Component | C2 | '2.5 | Novelty | Feature Stability & Recency Weighting | 2026-11-10 | 2026-12-20 | 41 |  | Planned
Component | C2 | '2.6 | XAI | Actionable vs Irremovable Feature Classification | 2026-11-20 | 2026-12-31 | 42 |  | Planned
Component | C2 | '2.7 | XAI | Counterfactual Candidate Generation | 2026-12-01 | 2027-01-15 | 46 |  | Planned
Component | C2 | '2.8 | Safety | Safety / Cost Evaluation of Counterfactuals | 2026-12-10 | 2027-01-31 | 53 |  | Planned
Component | C2 | '2.9 | Integration | LLM Narration & Dashboard Explanation | 2027-01-01 | 2027-02-15 | 46 |  | Planned
Component | C2 | '2.10 | Evaluation | User Explanation Evaluation | 2027-02-01 | 2027-03-15 | 43 |  | Planned
Component | C2 | '2.11 | Paper | Individual Paper Writing | 2027-01-15 | 2027-03-31 | 76 |  | Planned
Component | C3 | '3.1 | Research | Literature Review: Wearable Signal Processing | 2026-06-10 | 2026-08-20 | 72 |  | Planned
Component | C3 | '3.2 | Hardware | IoT Hardware & Sensor Selection | 2026-07-01 | 2026-08-31 | 62 |  | Planned
Component | C3 | '3.3 | Hardware | Sensor Data Acquisition Firmware | 2026-08-01 | 2026-09-30 | 61 |  | Planned
Component | C3 | '3.4 | Signal | Fast / Medium / Slow Signal Filters | 2026-09-01 | 2026-10-13 | 43 |  | Planned
Component | C3 | '3.5 | Signal | Windowing & Feature Extraction | 2026-09-15 | 2026-10-31 | 47 |  | Planned
Component | C3 | '3.6 | Novelty | Regression-Based Trend Extraction | 2026-10-01 | 2026-11-15 | 46 |  | Planned
Component | C3 | '3.7 | Signal | Aggregation & Z-Score Normalization | 2026-10-15 | 2026-11-30 | 47 |  | Planned
Component | C3 | '3.8 | ML | LSTM State-Trend Representation | 2026-11-01 | 2026-12-31 | 61 |  | Planned
Component | C3 | '3.9 | Integration | Device-to-API Gateway Integration | 2026-11-15 | 2027-01-15 | 62 |  | Planned
Component | C3 | '3.10 | Testing | Sensor Reliability & Stress Testing | 2026-12-01 | 2027-02-15 | 77 |  | Planned
Component | C3 | '3.11 | Paper | Individual Paper Writing | 2027-01-15 | 2027-03-31 | 76 |  | Planned
Component | C4 | '4.1 | Research | Literature Review: RAG, CRAG & PGxRAG | 2026-06-10 | 2026-08-20 | 72 |  | Planned
Component | C4 | '4.2 | Knowledge | Trusted Knowledge Source Collection | 2026-08-01 | 2026-09-30 | 61 |  | Planned
Component | C4 | '4.3 | RAG | Document Cleaning, Chunking & Metadata | 2026-09-01 | 2026-10-15 | 45 |  | Planned
Component | C4 | '4.4 | RAG | Embedding & ChromaDB Indexing | 2026-09-15 | 2026-10-31 | 47 |  | Planned
Component | C4 | '4.5 | RAG | Baseline RAG Retrieval | 2026-10-01 | 2026-11-15 | 46 |  | Planned
Component | C4 | '4.6 | Novelty | Genetic + Clinical Context Manager | 2026-10-15 | 2026-12-01 | 48 |  | Planned
Component | C4 | '4.7 | Novelty | Query Understanding / Decomposition | 2026-11-01 | 2026-12-15 | 45 |  | Planned
Component | C4 | '4.8 | Novelty | Corrective Retrieval & Confidence Gate | 2026-11-15 | 2027-01-15 | 62 |  | Planned
Component | C4 | '4.9 | RAG | Reranking & Evidence Grounding | 2026-12-01 | 2027-01-20 | 51 |  | Planned
Component | C4 | '4.10 | Safety | LLM Generation & Safety Checks | 2026-12-15 | 2027-02-15 | 63 |  | Planned
Component | C4 | '4.11 | Evaluation | RAGAS / Retrieval Evaluation | 2027-01-15 | 2027-03-01 | 46 |  | Planned
Component | C4 | '4.12 | Integration | GeneAir App / Portal Integration | 2027-01-20 | 2027-02-28 | 40 |  | Planned
Component | C4 | '4.13 | Paper | Individual Paper Writing | 2027-01-15 | 2027-03-31 | 76 |  | Planned